## Group 3 Grantt Chart
Group 3 Banking Project Schedule
PROJECT TITLE |  | Banking Service Development |  |  |  |  | GROUP NUMBER | [6 empty] | 3
GROUP MEMBER |  | Sungmo Koo, Daniel Rodriguez, Breanne Loo |  |  |  |  | DATE | [6 empty] | 2018-03-12
Important Notes: Week 7 (Phase 1 Complete), Week 11 (Phase 2 Complete), Week 16 (Final Project Presentation)
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | (Phase 1) Software Requirements Specification
1.1 | Purpose | All | 2024-02-13 | 2024-02-15 | 2 | 100% | bar: WEEK 5 T; WEEK 5 R; WEEK 6 F
1.2 | Overall Description | All | 2024-02-13 | 2024-02-15 | 2 | 100% | bar: WEEK 5 T; WEEK 5 R; WEEK 6 F
1.3 | Specific Requirements | All | 2024-02-16 | 2024-02-18 | 2 | 100% | bar: WEEK 6 F
1.4 | Non-Functional Requirements | All | 2024-02-21 | 2024-02-22 | 1 | 100% | bar: WEEK 6 W to WEEK 6 F
1.5 | Use Case Specifications | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W
1.5 | Class & Sequence Diagrams | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W
1.6 | Use Case Diagrams | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W
2 | (Phase 2) Project Design Phase
2.1 | System Architecture Design | TBD | 2024-03-04 | 2024-03-08 | 4 | Not started yet | bar: WEEK 6 F
2.2 | Detailed Design | TBD | 2024-03-09 | 2024-03-12 | 3 | Not started yet | bar: WEEK 6 F
2.3 | UI Design | TBD | 2024-03-10 | 2024-03-20 | 0 | Not started yet | bar: WEEK 6 F
2.4 | Interface Design | TBD | 2024-03-21 | 2024-03-28 | 0 | Not started yet | bar: WEEK 6 F
3 | (Final) Project Implementation
3.1 | Common Requirments | TBD | 2024-03-10 | 2024-03-12 | 0 | Not started yet | bar: WEEK 6 F
3.2 | User Module | TBD | 2024-03-13 | 2024-03-15 | 0 | Not started yet | bar: WEEK 6 F
3.2.1 | Bank User Module | TBD | 2024-03-16 | 2024-03-18 | 0 | Not started yet | bar: WEEK 6 F
3.2.2 | Teller User Module | TBD | 2024-03-19 | 2024-03-20 | 0 | Not started yet | bar: WEEK 6 F
3.3 | Oner User Module | TBD | 2024-03-20 | 2024-03-22 | 0 | Not started yet | bar: WEEK 6 F
3.3.1 | ATM Module | TBD | 2024-03-23 | 2024-03-28 | 0 | Not started yet | bar: WEEK 6 F
4 | Final Phase
4.1 |  |  |  |  | 0 | Not started yet | bar: WEEK 6 F
4.2 |  |  |  |  | 0 | Not started yet | bar: WEEK 6 F
4.3 |  |  |  |  | 0 | Not started yet | bar: WEEK 6 F
4.4 | Final Testing |  |  | 2024-05-02 | 0 | Not started yet | bar: WEEK 6 F