## Group 3 Grantt Chart
Group 3 Banking Project Schedule
PROJECT TITLE |  | Banking Service Development |  |  |  |  | GROUP NUMBER | [6 empty] | 3
GROUP MEMBER |  | Sungmo Koo, Daniel Rodriguez, Breanne Loo, Dongping Guo |  |  |  |  | DATE | [6 empty] | 2018-03-12
Important Notes: Week 7 (Phase 1 Complete), Week 11 (Phase 2 Complete), Week 16 (Final Project Presentation)
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | (Phase 1) Software Requirements Specification
1.1 | Purpose | All | 2024-02-13 | 2024-02-15 | 2 | 100% | bar: WEEK 5 T; WEEK 5 R; WEEK 9 T; WEEK 9 R
1.2 | Overall Description | All | 2024-02-13 | 2024-02-15 | 2 | 100% | bar: WEEK 5 T; WEEK 5 R; WEEK 9 T; WEEK 9 R
1.3 | Specific Requirements | All | 2024-02-16 | 2024-02-18 | 2 | 100% | bar: WEEK 6 F; WEEK 9 T; WEEK 9 R
1.4 | Non-Functional Requirements | All | 2024-02-21 | 2024-02-22 | 1 | 100% | bar: WEEK 6 W to WEEK 6 R; WEEK 9 T; WEEK 9 R
1.5 | Use Case Specifications | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W; WEEK 9 T; WEEK 9 R
1.5 | Class & Sequence Diagrams | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W; WEEK 9 T; WEEK 9 R
1.6 | Use Case Diagrams | All | 2024-02-23 | 2024-02-28 | 5 | 100% | bar: WEEK 6 F to WEEK 7 W; WEEK 9 T; WEEK 9 R
2 | (Phase 2) Project Design Phase
2.1 | Project Schedul (Gantt Chart) | Sungmo | 2024-03-12 | 2024-03-27 | 15 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R
2.2 | System Overview and Architecture | Daniel | 2024-03-12 | 2024-03-27 |  | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R
Dongping | bar: WEEK 9 T; WEEK 9 R
2.3 | System Architecture Diagram | Daniel | 2024-03-12 | 2024-03-27 |  | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R
Dongping | bar: WEEK 9 T; WEEK 9 R
2.2 | Class Diagrams | bar: WEEK 9 T; WEEK 9 R
2.2.1 | User Class | Daniel | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R; WEEK 11 R
2.2.2 | Teller Class | Sungmo | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R; WEEK 11 R
2.2.3 | ATM Class | Breanne | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R; WEEK 11 R
2.2.4 | Account Class | Daniel | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R; WEEK 11 R
2.2.5 | Server Class | Dongping | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R; WEEK 11 R
2.2 | Sequence Diagrams | bar: WEEK 9 T; WEEK 9 R
2.2.1 | User Class | Daniel | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.2.2 | Teller Class | Sungmo | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.2.3 | ATM Class | Breanne | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.2.4 | Account Class | Daniel | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.2.5 | Server Class | Dongping | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.3 | Use Cases | TBD | bar: WEEK 9 T; WEEK 9 R
2.3.1 | User Class | Daniel | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F
2.3.2 | Teller Class | Sungmo | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F
2.3.3 | ATM Class | Breanne | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F
2.3.4 | Account Class | Daniel | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F
2.3.5 | Server Class | Dongping | 2024-03-14 | 2024-03-25 | 11 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F
2.4 | Use Case Diagrams | bar: WEEK 9 T; WEEK 9 R
2.4.1 | User Class | Daniel | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.4.2 | Teller Class | Sungmo | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.4.3 | ATM Class | Breanne | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.4.4 | Account Class | Daniel | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.4.5 | Server Class | Dongping | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.5 | UI Diagrams | Breanne | 2024-03-12 | 2024-03-25 | 13 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
2.6 | Editing SRS | All | 2024-03-12 | 2024-03-27 | 15 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 10 R to WEEK 10 F; WEEK 11 R
3 | Implementation Phase
3.1 | Server Class | Dongping | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.2 | User Class | Daniel | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.3 | Bank User Class | Daniel | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.3.1 | Bank Account Class | Sungmo | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.4 | Teller Class | Sungmo | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
Daniel | bar: WEEK 9 T; WEEK 9 R
3.4.1 | Teller Client | Sungmo | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 14 T; WEEK 14 R
Daniel | bar: WEEK 9 T; WEEK 9 R
Dongping | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.5 | Admin Teller Class | Daniel | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.6 | ATM Class | Breanne | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.6.1 | ATM Client | Breanne |  |  |  | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.7 | Message Class | Dongping | 2024-04-09 | 2024-04-16 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 13 T to WEEK 16 T
3.8 | Teller GUI | Dongping | 2024-04-23 | 2024-04-28 | 5 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 14 R to WEEK 14 F; WEEK 15 T to WEEK 16 T
3.9 | ATM GUI | Breanne | 2024-04-23 | 2024-04-28 | 5 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 14 R to WEEK 14 F; WEEK 15 T to WEEK 16 T
3.10. | Github Setup Session | Dongping | 2024-04-09 | 2024-04-09 | 1 | 100% | bar: WEEK 9 T; WEEK 9 R
3.11 | JUnit Test | Daniel | 2024-04-23 | 2024-04-30 | 7 | 100% | bar: WEEK 9 T; WEEK 9 R; WEEK 14 R to WEEK 14 F; WEEK 15 T to WEEK 16 T